## Sheet1
| Question | Answer | Dated: Jan 17 2023
1 | Please confirm that Bldg 936 is not a part of the project scope. | Correct. Building 936 is not part of the project scope.
2 | It is unclear in the documents and the site visit which buildings have power, gas, and other utilities connected. Shall we assume that the utilities at each building will need to be disconnected and capped? | Yes.
3 | Please provide photos of Bldg 1471 to include exterior, the interior truss structure, a view looking into the interior from the end that is collapsing, and the loading dock/ramp. | Attached to Amendment.
4 | Please provide photos of the exterior and interior of Bldg 1494, 2006, 2204. Please include photos of the roof truss structure for Bldg 2204. | Attached to Amendment.
5 | Most of the earth-covered structures are similar. Will you please provide exterior and interior photos of one of the typical structures? | Attached to Amendment. Contractor is responsible to ascertain characteristics specific to each structure.
6 | Can you provide a drawing for any of the earth-covered structures? | No.
7 | Is there any preference for the order of the building demolition? | No.
8 | Can the buildings be demolished simultaneously? | Yes.
9 | On page 2 of the scope of work sec. 2.0 says building 936 is one of the buildings to be demolished? Does this building get demolished and if so could the Government provide an asbestos/lead survey inspection report? | Building 936 does not get demolished under this scope of work.
10 | Several asbestos survey inspection reports have transite water pipe, steam line rickwell with black coating, and steam pipe insulation located under ground/unknown. Each material says 200 linear feet. Does the government want the abatement contractor to bid off the measurements listed on the asbestos/ lead survey inspection report that has been provided? | Reference Section 2.7 of the Statement of Work.
11 | No door sweeps are sampled on any of the buildings to be demolished? On past projects in the MSA areas we have encountered asbestos door sweeps. Can the government verify if any suspect asbestos door sweeps are present on any of these buildings? | Reference Section 2.7 of the Statement of Work.
12 | The asbestos/lead survey inspection reports for building 2107, 2131, 2132, 2138, 2206, 2204, 2207, & 2227 mention transite water pipe, rickwell steam pipe, & steam pipe insulation listed as underground/unknown with linear footages. Can the government verify pipe sizes for the asbestos abatement contractor to bid off of? The size of the pipe can impact abatement costs. | Reference Section 2.7 of the Statement of Work.
13 | Can the government clarify work days, and hours that can be worked in the MSA 1 & 2 areas for this project? | Monday - Thursday 0700-1600
14 | In section 2.4 demolition of structures, it states that with permission by the Fire Department & American Water we can utilize water from approved fire hydrants. Can the government provide a map of approved fire hydrants that can be utilize for this project? | Contractor shall coordinate with American Water for a map of approved fire hydrants that can be utilized for this project.
15 | I have looked for the utility drawings showing the site utilities and what is connected to each of the building but I don't see that file. Can you provide that information so we know what needs to be disconnected at each building? | Reference Section 2.2 of the Statement of Work. Utility files attached to Amendment. |  | Does not appear the building utilities were included with the RFP. They are on SP
16 | Is there a location at Hill AFB where we can dispose of the dirt from the buildings or do we need to remove it off the base? | Dispose of excess dirt off base.
17 | Please provide photos of all buildings and utilities?
18 | Have the soils at each Demo sites been tested for lead contamination? | No.
19 | Will a 6’ high chain link temporary chain link fence or just a plastic snow fence with t-post be required at each location to be demolished per SOW 2.14? | The contractor shall construct a temporary barrier around each work site.
20 | Please provide all site utility maps for each demo location. | Reference Section 2.2 of the Statement of Work. Utility files will be sent in an Amendment.
21 | Do any of the demo site require ground clean-up of transite materials that may have become loosen by weather? | Contractor to determine the full extent of abatement prior to bid.
22 | The SOW states in section 2.2 utilities are to be removed within the footprint of the site map. Please provide a site map for each site or a given distance require to remove the utilities. | Reference Section 2.2 of the Statement of Work. Utility files will be sent in an Amendment.
23 | Will the free zone be able to be broken up in phases as well as the demo of each site? | Free Zones shall be designated for MSA I and MSA II.
24 | On page 2 of the scope of work sec. 2.0 says building 936 is one of the buildings to be demolished. Does this building get demolished and if so, could the Government provide an asbestos/lead survey inspection report? | Reference Question 9.
25 | Several asbestos survey inspection reports have transite water pipe, steam line with Rickwell black coating, and steam pipe insulation located underground/unknown. Each material says 200 linear feet. Does the government want the abatement contractor to bid off the measurements listed on the asbestos/ lead survey inspection report that has been provided? | Reference Question 10.
26 | No door sweeps are sampled on any of the buildings to be demolished. On past projects in the MSA areas we have encountered asbestos door sweeps. Can the government verify if any suspect asbestos door sweeps are present on any of these buildings? | Reference Question 11.
27 | The asbestos/lead survey inspection reports for building 2107, 2131, 2132, 2138, 2206, 2204, 2207, & 2227 mention transite water pipe, Rickwell coating steam pipe, & steam pipe insulation listed as underground/unknown with linear footages. Can the government verify pipe sizes for the asbestos abatement contractor to bid off? The size of the pipe can impact abatement costs. | Reference Question 12.
28 | Can the government clarify workdays, and hours that can be worked in the MSA 1 & 2 areas for this project? | Reference Question 13.
29 | In section 2.4 demolition of structures, it states that with permission by the Fire Department & American Water we can utilize water from approved fire hydrants. Can the government provide a map of approved fire hydrants that can be utilize for this project? | Reference Question 14.
30 | The asbestos report has a linear foot of pipe. Are we to assume for bidding purposes that, These are all the plumbing utilities feeding the building. (Gas, water, sewer, steam, condensate, etc. if listed? That quantities listed will get us to the manhole or the point of demo, and anything after that will be added cost later. (Gas, water, sewer, steam, condensate, etc.) | Reference Section 2.7 of the Statement of Work.
31 | The RFP states that 0% of design has been included by the government with this FOPR, however there is nothing in the bid documents that requires a design of any kind. Please confirm what design drawings, specs, etc. are expected for this project? | No design is required for this project. Standard specifications have been included.
32 | Many of the hazmat reports included in the RFP states there are 200Lf lengths of transite water pipe but can’t be verified on site during the site walk. Please confirm all bidding contractors are to only bid the quantities posted on this report and that anything found over and above that will be a modification after award? | Reference Section 2.7 of the Statement of Work.
33 | Some of the earth covered storage magazines that were toured as part of this RFP were labeled as “Fallout Shelters.” In addition to what is recorded in the hazmat reports, are bidding contractors to assume that there is a potential for chemicals or dangerous agents to have been stored at these locations at a previous time? | "Fallout Shelter" is defined as a building or other structure designed to protect people from radioactive fallout.
34 | On page 2 of the scope of work sec. 2.0 says building 936 is one of the buildings to be demolished? Does this building get demolished and if so could the Government provide an asbestos/lead survey inspection report? | Reference Question 9.
35 | Several asbestos survey inspection reports have transite water pipe, steam line rickwell with black coating, and steam pipe insulation located under ground/unknown. Each material says 200 linear feet. Does the government want the abatement contractor to bid off the measurements listed on the asbestos/ lead survey inspection report that has been provided? | Reference Question 10.
36 | No door sweeps are sampled on any of the buildings to be demolished? On past projects in the MSA areas we have encountered asbestos door sweeps. Can the government verify if any suspect asbestos door sweeps are present on any of these buildings? | Reference Question 11.
37 | The asbestos/lead survey inspection reports for building 2107, 2131, 2132, 2138, 2206, 2204, 2207, & 2227 mention transite water pipe, rickwell steam pipe, & steam pipe insulation listed as underground/unknown with linear footages. Can the government verify pipe sizes for the asbestos abatement contractor to bid off of? The size of the pipe can impact abatement costs. | Reference Question 12.
38 | Can the government clarify work days, and hours that can be worked in the MSA 1 & 2 areas for this project? | Reference Question 13.
39 | In section 2.4 demolition of structures, it states that with permission by the Fire Department & American Water we can utilize water from approved fire hydrants. Can the government provide a map of approved fire hydrants that can be utilize for this project? | Reference Question 14.
40 | The SOW paragraph 2.0 states that we are to have a “restoration of the site to a specified condition.” What is that specified condition? The paragraph also calls out following “grading and proper drainage, as per attached specifications” but those have not been included in this RFP. Will the government please provide the missing specifications sections as well as any other information we are to follow on this? | Each site shall be leveled out and graded to match the existing adjacent grades in a manner that will not cause excess stormwater runoff or pooling. Areas left after demolition shall be fully restored to match existing adjacent grades and vegetation specified by the reseeding requirements for Hill AFB found in the attached “Required Airfield and MSA seed mix.pdf”. |  | Uploaded to SP
41 | The SOW paragraph 2.0 states that “areas left after demolition shall be fully restored to match existing adjacent grades and vegetation specified by the reseeding requirements for Hill AFB found in the attached “Required Airfield and MSA seed mix.pdf.”” This document was not included in the RFP nor was it listed on the FOPR. Would the government please provide this missing information? | “Required Airfield and MSA seed mix.pdf” will be attached to an Amendment.
42 | The SOW paragraph 2.2 at the top of page 5 says “the contractor is required to demolish any utilities within the project limits that are not indicated on the utility map, but would normally be expected for a complete demolition project.” If scope is discovered that is not labeled anywhere or on any drawing or report than it would be a differing site condition. Yes we would be able to get it removed as stated, but it would be an additional cost to the government | No question asked.
43 | The SOW paragraph 2.2 states that “During demolition the construction contractor shall notify the 75 CEG surveyor before backfilling any trenched to allow for As-Built survey of alignment.” Does this mean that the government will be supplying the survey and as-built recording work and that the bidding contractors will not need to cover that scope? | Yes.
44 | The SOW paragraph 2.2 states “The salvage, demolition and debris removal process for the building shall not begin until the facility is inspected with 75CEG/CENM project management personnel and all connecting utilities are shut down, disconnected, or isolated from the facility in a manner satisfactory to the project management personnel, the Civil Engineering interior/exterior electric shop, plumbing shop, American Water utility company, HVAC shop, Fire Department personnel, and Base Safety.” This statement appears to be saying two different things; building inspection prior to demolition by 75CEG/CENM as well as either inspection or coordination and scheduling with the other organizations mentioned. Please confirm if the other organizations mentioned also need to be part of the inspection prior to demolition? | The contractor shall coordinate the removal of all utilities with the organizations mentioned. Demolition of the building and debri removal shall not begin until after utilties have been removed and inspected by 75CEG/CENM project management personnel.
45 | Some of the buildings toured during the site walk still had visible items being stored in them whether it be pallets, explosives, and other miscellaneous items. Please confirm that ALL explosives will be removed prior to work beginning and that all other items can be simply coordinated with 75CEG/CENM prior to work beginning? | All explosives shall be removed prior to work beginning. All other items shall be removed as part of the demolition.
46 | The SOW paragraph 2.7 states “A government representative certified as an asbestos inspector with 75 CES/CEOHA will provide this visual inspection. An independent, third-party consulting firm shall run the aggressive air clearance samples…daily abatement project documentation/logs and all air monitoring results must be submitted to the 75CES/CEOHA office at completion of the project. Please confirm that this is the case and that the government has a certified individual for this process? | The contractor is responsible to provide an independent, third-party consulting firm to run air clearance samples.
47 | On page 2 of the scope of work sec. 2.0 says building 936 is one of the buildings to be demolished? Does this building get demolished and if so could the Government provide an asbestos/lead survey inspection report? | Reference Question 9.
48 | Several asbestos survey inspection reports have transite water pipe, steam line rickwell with black coating, and steam pipe insulation located underground/unknown. Each material says 200 linear feet. Does the government want the abatement contractor to bid off the measurements listed on the asbestos/ lead survey inspection report that has been provided? | Reference Question 10.
49 | No door sweeps are sampled on any of the buildings to be demolished? On past projects in the MSA areas we have encountered asbestos door sweeps. Can the government verify if any suspect asbestos door sweeps are present on any of these buildings? | Reference Question 11.
50 | The asbestos/lead survey inspection reports for building 2107, 2131, 2132, 2138, 2206, 2204, 2207, & 2227 mention transite water pipe, rickwell steam pipe, & steam pipe insulation listed as underground/unknown with linear footages. Can the government verify pipe sizes for the asbestos abatement contractor to bid off of? The size of the pipe can impact abatement costs. | Reference Question 12.
51 | Can the government clarify work days, and hours that can be worked in the MSA 1 & 2 areas for this project? | Reference Question 13.
52 | In section 2.4 demolition of structures, it states that with permission by the Fire Department & American Water we can utilize water from approved fire hydrants. Can the government provide a map of approved fire hydrants that can be utilized for this project. | Reference Question 14.
53 | BLDG 1471 The building was falling down, and it was hard to see if there were utilities. Does building 1471 have any plumbing utilities going to it? (Gas, water, sewer, etc.) | Reference Section 2.2 of the Statement of Work. Utility files will be sent in an Amendment.
54 | BLDG 1494 Can you confirm that there are no underground plumbing utilities? If there are utilities, for bidding purposes how many feet do you want us to demo. There was a foot of snow and there are no as-builts to show us how far to demo too. | Reference Section 2.2 of the Statement of Work. Utility files will be sent in an Amendment.
55 | BLDG 2006 Can you confirm that there are no underground plumbing utilities? If there are utilities, for bidding purposes how many feet do you want us to demo. There was a foot of snow and there are no as-builts to show us how far to demo too. | Reference Section 2.2 of the Statement of Work. Utility files will be sent in an Amendment.
56 | BLDG 2107 The scope of work doesn’t call out how far away the manhole or the main is. For bidding purposes how many feet do you want us to demo. There was a foot of snow and there are no as-builts to show us how far to demo too. (Gas, water, sewer, steam, condensate, etc.) | Reference Section 2.2 of the Statement of Work. Utility files will be sent in an Amendment.
57 | BLDG 2108 The scope of work doesn’t call out how far away the manhole or the main is. For bidding purposes how many feet do you want us to demo. There was a foot of snow and there are no as-builts to show us how far to demo too. (Gas, water, sewer, steam, condensate, etc.) | Reference Section 2.2 of the Statement of Work. Utility files will be sent in an Amendment.
58 | BLDG 2131 The scope of work doesn’t call out how far away the manhole or the main is. For bidding purposes how many feet do you want us to demo. There was a foot of snow and there are no as-builts to show us how far to demo too. (Gas, water, sewer, steam, condensate, etc.) | Reference Section 2.2 of the Statement of Work. Utility files will be sent in an Amendment.
59 | BLDG 2132 The scope of work doesn’t call out how far away the manhole or the main is. For bidding purposes how many feet do you want us to demo. There was a foot of snow and there are no as-builts to show us how far to demo too. (Gas, water, sewer, steam, condensate, etc.) | Reference Section 2.2 of the Statement of Work. Utility files will be sent in an Amendment.
60 | BLDG 2138 The scope of work doesn’t call out how far away the manhole or the main is. For bidding purposes how many feet do you want us to demo. There was a foot of snow and there are no as-builts to show us how far to demo too. (Gas, water, sewer, steam, condensate, etc.) | Reference Section 2.2 of the Statement of Work. Utility files will be sent in an Amendment.
61 | BLDG 2204 The scope of work doesn’t call out how far away the manhole or the main is. For bidding purposes how many feet do you want us to demo. There was a foot of snow and there are no as-builts to show us how far to demo too. (Gas, water, sewer, steam, condensate, etc.) | Reference Section 2.2 of the Statement of Work. Utility files will be sent in an Amendment.
62 | BLDG 2206 The scope of work doesn’t call out how far away the manhole or the main is. For bidding purposes how many feet do you want us to demo. There was a foot of snow and there are no as-builts to show us how far to demo too. (Gas, water, sewer, steam, condensate, etc.) | Reference Section 2.2 of the Statement of Work. Utility files will be sent in an Amendment.
63 | BLDG 2207 The scope of work doesn’t call out how far away the manhole or the main is. For bidding purposes how many feet do you want us to demo. There was a foot of snow and there are no as-builts to show us how far to demo too. (Gas, water, sewer, steam, condensate, etc.) | Reference Section 2.2 of the Statement of Work. Utility files will be sent in an Amendment.
64 | BLDG 2227 The scope of work doesn’t call out how far away the manhole or the main is. For bidding purposes how many feet do you want us to demo. There was a foot of snow and there are no as-builts to show us how far to demo too. (Gas, water, sewer, steam, condensate, etc.) | Reference Section 2.2 of the Statement of Work. Utility files will be sent in an Amendment.
65 | What level of design is anticipated for this contract? Are construction demolition drawing required for base records? | No drawings are required for this project.
66 | If drawings are required, can typical demolition drawings be done to account for similar conditions, or will each building need to be individually documented? | Na drawings done similar each be project.
67 | Are existing record drawings available for the contractors to use in determining a proposal? | Record drawing available have been provided.
68 | Are there any photos that are available to the contractors? | Photos requested during the RFI period are attached.
69 | The scope of work indicated that the contractor is to return the site of each building back to grade. Several of the buildings (specifically the munition storage buildings) are constructed up on a dirt platform or plinth. Is it the government's intention that the plinth be leveled down to the surrounding grade, or that the plinth elevation counts as the grade elevation that needs to be maintained? | Scope of work indicates, "Each site shall be leveled out and graded to match the existing adjacent grades in a manner that will not cause excess stormwater runoff or pooling."