## Sheet1
SCHEDULE OF MATERIAL SUBMITTALS | [8 empty] | CAPITAL PROJECT NUMBER: |  |  |  |  | PROJECT TITLE: MSA Multiple Building Demolition | [6 empty] | SOLICITATION / CONTRACT NO.:
Date: 19 August 2022
LINE NUMBER | ITEM OR DESCRIPTION OF ITEM, CONTRACT REFERENCE, TYPE OF SUBMITTAL | NUMBER OF COPIES REQUIRED
|  | CERTIFICATE OF COMPLIANCE | SHOP DRAWINGS | SAMPLES | COLOR SELECTIONS | MANUFACTURER'S RECOMMENDATION | MANUFACTURER'S WARRANTY | CATALOG DATA | OPERATING INSTRUCTIONS | SCHEDULES, LISTINGS, REPORTS, PLANS | TECHNICAL DATA | TEST REPORTS | FIELD REPORTS | REQUIRED SUBMISSION DATE | DATE RECEIVED IN CONTRACTING | DATE TO CIVIL ENGINEERING | RETURN TO SUSPENSE DATE | NUMBER OF SUBMITTALS | DATE CONTRACTOR NOTIFIED |  | CONTRACTOR RESUBMITTAL | FINAL APPROVAL DATE | REMARKS
[19 empty] | APPROVED | DISAPPROVED
1 | DEMOLITION PLAN | [8 empty] | X | [7 empty] | 13
2 | QUALITY CONTROL PLAN | [8 empty] | X | [7 empty] | 1
3 | SAFETY INSPECTION DAILY LOG | [11 empty] | X |  |  |  |  | 52
4 | ENVIRONMENTAL PROTECTION PLAN | [8 empty] | X | [7 empty] | 1
5 | STORM WATER POLLUTION PREVENTION PLAN Checklist | X | [7 empty] | X | [7 empty] | 1
6 | ACCIDENT PREVENTION PLAN | [8 empty] | X | [7 empty] | 1
7 | LICENSE CERTIFICATES | X | [15 empty] | 1
8 | GRADING & RESEEDING PLAN | [8 empty] | X | [7 empty] | 13
9 | DUMP & RECYCLING MANAFEST/WEIGHT TICKETS | [9 empty] | X |  | X |  |  |  |  | Monthly
10 | DD FOR 1354 (Draft-Interim-Final) | [9 empty] | X | [6 empty] | 3
11 | 10 WORKING-DAY NOTIFICATION OF DEMOLITION (UTAH DIVISION OF AIR QUALITY) (DAQA-424-12) | X | [15 empty] | 1
12 | DIVERSION PLAN | [8 empty] | X | [7 empty] | 1
13 | WEEKLY SAFETY MEETING MINUTES | [11 empty] | X |  |  |  |  | 52
14 | QUALITY CONTROL DAILY LOG | [11 empty] | X |  |  |  |  | 52
15 | SITE LAYDOWN PLAN | [8 empty] | X | [7 empty] | 13
16 | Existing Conditions Report | [11 empty] | X |  |  |  |  | 13
17
18
19
20
21
22
23
24
25
26
27
28